GridV2

Audit, Roadmap, Pricing & Subagent Workflow Plan

Prepared for John Nguyen · May 20, 2026

# 1. Summary

GridV2 is shifting from a public entertainment-only practice board to a private invite-only sportsbook simulator for a small group (1–200 users) running on live Pinnacle pregame odds. No real money, no public signup, no payment processor. Each user gets an account created by an admin (you or an agent) and tracks a simulated bankroll against real lines.

This document locks in the scope shift, the new tech stack, the monthly cost picture, and the workflow you'll use to ship the MVP in 2–3 months. It also lays out the optional Claude Max 20x + overnight subagent fleet so you can see the tradeoff before you upgrade.

### Three things to decide before buying anything

- OddsPapi tier: Normal ($57/mo, ~5K requests, fits a ~5-min refresh) vs Dev ($114/mo, ~100K requests, comfortable 1-min refresh). Recommendation: start Normal, upgrade if you hit the cap.

- Subagent intensity: stay on current Claude plan (slower, $0 extra) or upgrade to Max 20x ($200/mo) to add a 4-agent overnight fleet (~5–6 wk MVP instead of 10–12 wk).

- Teammate: solo with agents, or add a parallel human stream. Roadmap is written so either works — but if a teammate is joining, define their lane in week 1.

# 2. Project Identity (Updated Scope)

### Was

- Public, entertainment-only Tailwind v4 + Vite practice board

- Mock data fixture + optional user-paste OddsPapi key in browser

- Cloudflare Pages static deploy, no backend

### Is becoming

- Private, invite-only sportsbook simulator for 1–200 trusted users

- Live Pinnacle pregame odds across Big 6 sports (Soccer, Basketball, Tennis, Baseball, American Football, Ice Hockey) — covers all current GridV2 sports plus Soccer/Tennis

- Real backend: Node + TypeScript on a VPS, with Postgres for accounts/balances/bet history

- Admin-created accounts (no self-signup), per-user sim bankrolls, persistent state

- Cloudflare Pages still hosts the static frontend; VPS hosts the API + DB + agent runner

### Stays the same (hard rules)

- No real money handling. No bet placement against real books. No payment processor.

- Entertainment-only disclaimer prominent. 18+ implied (private group, no public marketing).

- Tailwind v4 + Vite frontend stack stays. Build tools allowed. Vanilla JS — no React/Vue.

- BetSim v1, BetCalc, bet-tools remain locked single-file legacy projects. Untouched.

# 3. Tech Stack

### Frontend (unchanged)

- Tailwind v4 + Vite 6 + vanilla JS (ES modules)

- Hosted on Cloudflare Pages, auto-deploy on push to main

- Repo: github.com/bungph3-inspired/gridv2

- Live URL: gridv2.pages.dev (custom domain optional — see signup checklist)

### Backend (new)

- Node 20 + TypeScript

- Framework: Hono (faster, lighter than Express; runs on Node, Bun, edge — gives you flexibility if you later move parts of it to Cloudflare Workers)

- DB: Postgres 16, self-hosted on the VPS. Drizzle ORM for type-safe queries.

- Auth: Roll-your-own admin-issued credentials. Argon2 password hashing. Session cookies (HttpOnly, Secure, SameSite=Lax). No self-signup endpoint at all.

- Odds pipeline: Cron worker polls OddsPapi on a schedule, writes to a snapshots table, exposes a read-only /odds endpoint to the frontend. API key never leaves the server.

- Reverse proxy: Caddy (auto-HTTPS via Let's Encrypt) in front of Node. Simple Caddyfile, no Nginx complexity.

- Process manager: systemd units (one for the API, one for the cron worker). Restart on failure, logs to journalctl.

### Agent runtime (new, optional)

- Claude Code installed on the same VPS, authenticated via Claude Max 20x token

- Cron triggers overnight sessions; output is git branches + PRs against main

- 4 specialized agents: Architect (planning/specs), Coder (implementation), Tester (writes + runs tests), Reviewer (code review on PRs)

# 4. Pricing Breakdown

Three scenarios — Lean (everything you can possibly defer), Recommended (the sane starting point), Full (Max 20x + Dev-tier data + extras). Numbers are USD/month unless noted.

## Scenario A — Lean ($67/mo)

You and agents on your current Claude plan. No overnight fleet. Smallest VPS, Normal-tier OddsPapi. Skip everything optional.

| Item | Tier / Spec | Monthly | Notes |
| --- | --- | --- | --- |
| OddsPapi | Pinnacle pregame + Big 6, Normal (×1, ~5K req) | $57.00 | Tight on quota. 5-min refresh OK during US hours. |
| VPS — Hetzner CPX22 (US) | 3 vCPU · 4 GB · 80 GB NVMe | $9.60 | Runs Node + Postgres + cron + optional agent runner. |
| Domain (Cloudflare Registrar) | .com, annual | $0.87 | $10.44/yr ÷ 12. Wholesale, no markup. |
| Auth / Email / Monitoring | Self-host + Sentry/BetterStack free | $0.00 | Free tiers cover 1–200 users comfortably. |
| Claude plan | Current Max (no upgrade) | $0.00 | No additional cost over what you pay today. |
| Total |  | $67.47 |  |

## Scenario B — Recommended ($267/mo) ★

Adds Claude Max 20x for the 4-agent overnight fleet. Same OddsPapi tier and VPS as Lean — the data + infra needs don't actually change, just the dev velocity.

| Item | Tier / Spec | Monthly | Notes |
| --- | --- | --- | --- |
| OddsPapi | Pinnacle pregame + Big 6, Normal | $57.00 | Same as Lean. |
| VPS — Hetzner CPX22 (US) | 3 vCPU · 4 GB · 80 GB NVMe | $9.60 | Headless Claude Code coexists with app. Fine at 4 GB. |
| Domain | .com via Cloudflare | $0.87 |  |
| Auth / Email / Monitoring | Free tiers | $0.00 |  |
| Claude Max 20x | Overnight subagent fleet | $200.00 | ~110 productive hrs/wk vs ~40. Halves MVP timeline. |
| Total |  | $267.47 | Within your $500 budget. Best $/velocity trade. |

## Scenario C — Full ($381+/mo)

If 1-minute odds refresh matters (it usually doesn't for pregame), or you want production-grade monitoring + transactional email out of the gate.

| Item | Tier / Spec | Monthly | Notes |
| --- | --- | --- | --- |
| OddsPapi | Pinnacle pregame + Big 6, Dev (×2, ~100K req) | $114.00 | 1-min refresh comfortably. No quota worries. |
| VPS — Hetzner CPX32 (US) | 4 vCPU · 8 GB · 160 GB NVMe | $17.00 | Headroom for traffic + agent fleet + DB growth. |
| Domain | .com | $0.87 |  |
| Sentry Team | Error tracking, multi-seat | $26.00 | If teammate joins. |
| BetterStack paid | Uptime + log management | $29.00 | Optional. Free tier likely enough early. |
| Auth / Email | Free tiers (or Resend Pro $20 if scale) | $0.00 |  |
| Claude Max 20x | Subagent fleet | $200.00 |  |
| Total |  | $386.87 | Still under your $500 ceiling. |

### One-time costs (not monthly)

- Cloudflare domain registration: ~$10.44 first year, then annual

- Optional LLC formation (not recommended for private/invite-only): $50–500 depending on state

- Optional gaming-attorney 1-hour consult before any future scope change: $300–800

### Cost-by-decision table

| Item | Tier / Spec | Monthly | Notes |
| --- | --- | --- | --- |
| Stay on current Claude plan | no fleet | — | −$200/mo · MVP 10–12 wks |
| Upgrade to Max 20x | 4-agent overnight fleet | +$200 | MVP 5–6 wks · 110 hrs/wk parallel |
| Normal → Dev OddsPapi | 1-min refresh, 100K req | +$57 | Buy only if you hit Normal's quota wall |
| Live odds add-on (Pinnacle ×2) | in-game line moves | +$30 | Skip — sim is pregame-only by design |
| Player props (×1.5) | prop markets | +$15 | Skip — out of scope (your current sport set has no props in UI) |

# 5. Workflow Comparison — Current Plan vs. Max 20x + Fleet

See the diagram delivered alongside this doc (gridv2_workflow_current_vs_max20x.svg). The summary version:

### Scenario A — Current Claude Plan (solo)

- You work daytime hours (~7am–10pm PT) in Cowork sessions

- Single development stream — you, one Claude at a time

- Nights are dead — no work happens, no progress while you sleep

- ~40 productive hours/week. MVP at 2–3 month target: 10–12 weeks.

- Cost: $0 above current Claude plan. Simple.

### Scenario B — Max 20x + 4-Agent Fleet (recommended)

- Daytime (you): drive features, review last night's PRs, plan next night's batch

- Nighttime (fleet on VPS): 4 specialized agents work in parallel branches, open PRs against main

- CI runs tests on every PR. You wake up to a review queue, not a blank slate.

- ~110 productive hours/week (your ~40 + fleet's ~70 effective). MVP target: 5–6 weeks.

- Cost: +$200/mo Claude Max 20x. No additional VPS cost (same box runs the fleet).

### How the night shift actually runs

- Before sleeping, you commit a spec file (markdown) describing the night's work — e.g., "implement /api/odds GET endpoint with tests, branch feat/odds-endpoint"

- Cron triggers the Architect agent at 11pm PT — reads the spec, breaks it into tasks, files them as issues on the gridv2 repo

- Coder agent picks up issues sequentially, works in branches, opens PRs when done

- Tester agent writes/runs unit + integration tests on each PR

- Reviewer agent leaves review comments (style, edge cases, missing tests) — does NOT merge

- You wake up to: PR queue + Architect's morning briefing markdown — read, approve, request changes, or close

### Safety rails (non-negotiable)

- Agents only work on branches. main is locked — only you can merge.

- CI tests must pass before a PR is mergeable (GitHub branch protection).

- Agents have NO access to: production database, secrets file, billing systems (none yet, but principle holds).

- All agent activity is logged to a daily session log file you can scan in 5 min.

- Kill switch: a flag file on the VPS pauses the fleet immediately. Cron checks it before starting.

# 6. Subagent Fleet — Roles & Division of Labor

| Agent | Model | What it does | Output |
| --- | --- | --- | --- |
| Architect | Sonnet | Plans the night's work. Reads your spec, writes task breakdown, files GitHub issues. Writes morning briefing. | Specs · tasks · briefings |
| Coder | Sonnet | Implements one task at a time. Works in branch, follows project conventions, opens PR when done. | Branches · PRs |
| Tester | Haiku | Writes unit + integration tests for each PR. Runs the test suite. Flags failures. | Test files · CI runs |
| Reviewer | Sonnet | Reads PRs, leaves review comments, suggests improvements. Does NOT merge. | PR review comments |

### If a teammate joins

Treat them as a 5th independent stream, not as an agent replacement. They own a parcel of features end-to-end. Suggested splits:

- Backend lane: teammate owns API + DB + cron + auth. You own UI + product decisions. Cleanest.

- Frontend lane: teammate owns mobile polish + the agent.html dashboard. You own backend + integrations.

- Feature lane: teammate owns settle/grading + bet history. You own odds pipeline + live board.

Communication: a shared CLAUDE.md addendum in /projects/GridV2/ documenting current owners + open questions. Async-friendly so subagents can read it too.

# 7. Phased Roadmap (5–6 weeks with Max 20x · 10–12 weeks solo)

## Phase 0 — Foundation (Week 1)

Goal: every dependency provisioned, VPS booted, repo wired for branch-PR flow. No app code yet.

- Buy OddsPapi Normal tier ($57) — verify Pinnacle pregame + Big 6 + Normal request multiplier on the customizer (your screenshot shows exact $57)

- Email OddsPapi support: "Private invite-only app for 1–200 users, server-side proxy, never re-exposing raw data. Permitted under Starter?" Confirm before going live.

- Provision Hetzner CPX22 in Ashburn or Hillsboro. Add SSH key. Disable password login.

- Install: Caddy, Postgres 16, Node 20, pm2 or systemd, ufw firewall (only 22/80/443 open)

- Buy domain via Cloudflare Registrar (suggest gridv2.app or similar). Point at Cloudflare DNS.

- Wire branch protection on main: require PR, require passing CI

- Decide: upgrade to Claude Max 20x? If yes, install Claude Code on VPS, generate 1-year token, test a single agent run

- Update GridV2 PROJECT.md to reflect new scope (already in motion as part of this audit)

## Phase 1 — Backend MVP (Weeks 2–3)

Goal: API serves odds and per-user state. No UI changes yet.

- Postgres schema: users, sessions, sim_balances, placed_bets, odds_snapshots

- Auth: admin CLI to create user (username + bcrypt password), login endpoint, session cookie

- OddsPapi proxy: cron worker polls every 5 min during US sports active windows, writes odds_snapshots, /api/odds reads the latest snapshot

- Place-bet endpoint: validates user, deducts from balance, writes placed_bets row

- Settle worker: reads game results from OddsPapi (or manual entry initially), grades pending bets, returns winnings to balance

- Integration tests for every endpoint. Tester agent writes these overnight.

## Phase 2 — Frontend Integration (Weeks 3–4)

Goal: existing GridV2 UI talks to the new backend. API-key paste removed. Login screen added.

- Replace browser-side OddsPapi fetcher with calls to /api/odds (same shape if possible — minimize main.js changes)

- Add /login page (vanilla HTML, Tailwind v4) — credentials flow to /api/login

- Persist sim balance + placed bets to server, not localStorage (gradual migration — keep bs_* localStorage as legacy cache)

- Admin page (private, gated by env-var-set admin token): create user, view all balances, reset state

- Mobile + desktop both updated. Agent.html dashboard stays as-is (or pulls user stats from API).

## Phase 3 — Private Launch (Weeks 4–5)

Goal: invite the first 3–5 friends, gather feedback, fix what breaks.

- Admin creates accounts for initial group, hands out credentials privately

- Daily check: agent runs a usage report (who logged in, bets placed, errors thrown)

- Bug bash week — Reviewer agent flags edge cases, you triage

- Soft cap at 5 users until stability looks solid

## Phase 4 — Scale & Polish (Weeks 5–6)

Goal: handle the full 1–200 user range, mobile UX is smooth, ops are boring.

- Load-test API: simulate 200 concurrent users hitting /api/odds — confirm Postgres + Hono can handle it on the CPX22 (likely fine)

- Mobile polish: bottom-sheet animations, swipe-to-dismiss, haptic-style feedback

- Monitoring: Sentry catches errors, BetterStack pings uptime, daily digest email to you

- Backup: nightly pg_dump to a separate Hetzner storage box or B2 ($1/mo)

- Open up to remaining users on the invite list

## Phase 5 — Beyond MVP (optional, later)

- Group leaderboards (highest sim bankroll, longest win streak, biggest single win)

- Bet-of-the-day broadcast (admin posts a featured line, group reacts)

- Stats page (your own +EV vs actual results, like a personal report card)

- Native mobile shell (Capacitor or PWA) if anyone wants an icon on their home screen

# 8. Purchase + Signup Checklist (in order)

Do these top-to-bottom. Each step references its monthly cost and what to configure during signup.

### Step 1 — OddsPapi ($57/mo, ~5 min)

- Visit oddspapi.io/us/pricing

- Bookmakers: select Pinnacle Sports only. Leave Live and Player Props unchecked.

- Sports: select The Big 6 (Soccer, Basketball, Tennis, Baseball, American Football, Ice Hockey). Skip ESports.

- Requests: Normal (~5,000/mo). Verify subtotal shows $57.00.

- Pay, then go to dashboard and copy API key. Save in 1Password or similar — DO NOT commit to git.

- Email support: confirm private/invite-only server-side proxy use is permitted under Starter ToS.

### Step 2 — Hetzner VPS ($9.60/mo, ~15 min)

- Sign up at hetzner.com/cloud (Hetzner Cloud, not Hetzner Online dedicated)

- Create Server → Location: Ashburn (US East) or Hillsboro (US West, pick closest)

- Image: Ubuntu 24.04 LTS

- Type: CPX22 (Shared vCPU, 3 cores, 4 GB RAM, 80 GB NVMe)

- Add SSH key (generate one if you don't have one: ssh-keygen -t ed25519)

- Name: gridv2-prod-01

- Create & Buy — server provisions in ~30 sec

- First SSH in: apt update && apt upgrade -y, install ufw, allow 22/80/443, disable password auth in /etc/ssh/sshd_config

### Step 3 — Cloudflare Registrar Domain (~$10.44/yr, ~10 min)

- Cloudflare Dashboard → Domain Registration → Register Domain

- Search for gridv2.app, gridv2.io, or similar. .com if available, .app fine alternative.

- Add to cart, pay. WHOIS privacy is free + automatic.

- DNS records: A record api.<domain> → VPS IP. CNAME app.<domain> → gridv2.pages.dev.

### Step 4 — Claude Max 20x ($200/mo, ~5 min) — only if going Recommended

- claude.ai/settings/billing → upgrade to Max 20x

- Confirm 5-hour usage windows + Sonnet/Haiku access at higher quota

- On the VPS: install Claude Code (npm install -g @anthropic-ai/claude-code), run claude setup-token, paste the OAuth code into your local browser, copy the 1-year token back to the VPS as ANTHROPIC_TOKEN env var

- Test: ssh into VPS, run claude -p "echo test" — confirm output

### Step 5 — Supporting Services (free, ~30 min total)

- Sentry: signup, create gridv2 project (Node), copy DSN

- BetterStack: 1 uptime monitor on https://api.<domain>/health (you'll add this endpoint in Phase 1)

- GitHub branch protection: Settings → Branches → require PR + passing CI before merging to main

- GitHub Actions: a workflow that runs npm test + npm run build on every PR. Free for public/private personal repos.

### Step 6 — Decide on Teammate (sometime in Week 1)

- If yes: have a 30-min call. Confirm comp model (paid hourly, equity, learning). Get them a GitHub seat on the gridv2 repo (free for collaborators).

- Add their owned lane to PROJECT.md. They get their own branch namespace (e.g., friend/*) so PRs are visually attributed.

- If no for now: roadmap stays solo + agents. Revisit at Phase 3.

# 9. Risks & Open Questions

### Risks to plan for

- OddsPapi ToS: "redistribute as a standalone product" clause is ambiguous. Mitigation: email support before launch (Phase 0).

- Pinnacle latency/coverage: pregame-only excludes in-game lines. If users expect live odds in the sim, set expectations early in onboarding.

- Agent prompt drift: overnight agents producing low-quality PRs. Mitigation: tight spec format, Reviewer agent never merges, your morning review is the gate.

- Token cap on Max 20x: 4 parallel agents share the 5-hour rolling budget. Mitigation: stagger overnight runs (Architect 11pm, Coder 12am–5am sequential, Tester runs on PR open, Reviewer at 5am).

- VPS as single point of failure: nightly backups + a recovery runbook in /reference/ before launch.

### Open questions for you

- Domain name preference (gridv2.app vs alternative)?

- Hetzner Ashburn vs Hillsboro (closer to you in CA is Hillsboro)?

- Live odds for in-game lines — confirm pregame-only is acceptable, or budget for the Live ×2 add-on?

- Teammate yes/no/maybe — needs decision by end of Phase 0 to lock the roadmap

- Brand: GridV2 stays as the user-facing name, or rename for the private group?

# 10. Definition of "Done"

### MVP is live when…

- 3–5 invited users can log in with admin-issued credentials

- Each user sees live Pinnacle pregame odds for all Big 6 sports refreshed at least every 5 min

- Each user can place a sim bet (Straight, Parlay, Teaser, Reverse, If Bet) and see it on /my-bets

- When the underlying game settles, the bet auto-grades (or admin can manually grade) and the bankroll updates

- Mobile + desktop both work — no broken layouts, no console errors

- Uptime monitor green for 72 consecutive hours

- Kill switch tested — you can pause agents and revert a bad merge in under 5 minutes

# 11. Refinements (added 2026-05-20)

Updates from the follow-up planning conversation. These supersede the corresponding bullets in earlier sections — read these last.

## 11.1 Fleet path — three options on the table

You confirmed your Max 5x is sitting mostly idle on a typical day, which opens up a free-or-cheap fleet option. The Max 20x upgrade is no longer the default — it's a trigger-based upgrade if Path A doesn't keep up.

| Path | Claude plan | Add-on | Fleet schedule | MVP | When to pick |
| --- | --- | --- | --- | --- | --- |
| A — Overnight 2-agent ★ | Max 5x (current) | $0 | Coder + Reviewer · 12am–7am | 7–8 wks | Lowest risk · validates workflow |
| B — 1-agent 17.5hr daily | Max 5x (current) | $0 | Coder only · 12am–1pm + 7pm–11pm | 6–7 wks | More fleet hours, similar throughput, more cap pressure |
| C — Max 20x + 2-agent 17.5hr | Max 20x upgrade | +$100 | Coder + Reviewer · same schedule as B | 5–6 wks | Upgrade only if Path A hits cap consistently |

### Recommended sequence

- Start with Path A (overnight 2-agent on Max 5x). Zero cost. Lowest risk.

- Run for 2 weeks. Track in agent logs: token-cap hits, stalled mid-night PRs, tasks that need 2+ nights.

- If Path A consistently underperforms (you're wishing for more hours OR you're capped out), upgrade to Path C.

- Path B is documented for completeness but skipped — same productivity as A, more cap pressure.

## 11.2 Wager logger schedule

Wager logger runs MANUALLY for now. Same-day error correction (LOSE-LOSE flags, unfamiliar accounts, missing tickets) requires synchronous runs you can act on immediately. Batch API migration deferred until the audit catches fewer surprises (probably post-Phase 2 of GridV2 work).

- Token reservation on Max 5x: ~250K/day for wager logger (heavy days), drawn unpredictably across morning, afternoon, and evening batches

- Fleet cron checks for an active wager logger run before starting; pauses if one is in flight or just completed

- Future: Batch API migration costs ~$15/mo, frees the full 250K/day for fleet work. Triggered when extraction is stable enough to tolerate a half-day delay on logging.

## 11.3 Daily fleet schedule

Fleet runs throughout the day except during your project drive window (1pm-7pm PST). Updated from the original overnight-only assumption.

- 12am-1pm PST: Fleet active (overnight + morning review window)

- 1pm-7pm PST: Fleet paused, you drive

- 7pm-10:30pm PST: Fleet active (evening session)

- 10:30pm-11pm PST: Wager logger primary slot (if not run earlier)

- Hard pause at 12:55pm writes a session report so you know exactly what was in flight

- Fleet resumes at 7:05pm automatically

Per Path A (recommended start), this 17.5-hr window is served by 2 agents during overnight only at first. Path C unlocks the full 17.5-hr fleet.

## 11.4 Morning briefing system

New management surface designed to remove the burden of "what should I work on today" from you. Built today; lives in the workspace and surfaces automatically at session start.

### Files + structure

- Master briefing: ClaudeWorkSpace/briefings/latest.md (plus dated history)

- Per-project briefings: projects/<name>/briefings/latest.md (active projects only)

- Template reference: briefings/BRIEFING_TEMPLATE.md

### Standing instruction (already added to workspace CLAUDE.md)

At session start, Claude reads briefings/latest.md and presents it as the first response if it is less than 18 hours old. Skipped if you jump straight into a task or explicitly ask to skip the briefing.

### Producer evolution

- Now (pre-VPS): Claude writes briefings on demand at session start, or a Cowork scheduled task at 12:50pm PST while your PC is on

- Post-VPS: Architect agent’s closing task writes each per-project briefing; a 12:50pm aggregator rebuilds the master

- Same file format throughout. VPS migration is producer-only, no consumer changes

### Active project coverage

- Full briefings: GridV2, wager-logger, TCG, hedge-tools, discord-bridge, Pokeball, github-mcp-server

- Quiet (no-activity stub): BetSim, BetCalc, bet-tools, BetSim_Manual

- Not yet covered: wr_item_recon (needs PROJECT.md first)

## 11.5 Live workspace dashboard

Companion to the briefing. A pinnable Cowork artifact (id: workspace-dashboard) that pulls live GitHub state and shows project status cards. Updates on open via the Reload button. Use it as the at-a-glance "is everything OK" surface; use the briefing for narrative + decisions.

## 11.6 Open decisions before Phase 0 starts

- Pick Path A / B / C (default: A)

- Pick domain name (default: gridv2.app)

- Pick Hetzner region (Ashburn or Hillsboro. Hillsboro is closer to CA)

- Teammate yes/no/maybe (default: maybe. Plan flexible either way)

- OddsPapi ToS confirmation email. Must send before purchasing.

## 11.7 Phase 0 decisions locked (2026-05-22)

Final answers on the six items in §11.6, captured live in a session with John on 2026-05-22. These supersede the §11.6 defaults and the 5/21 GridV2 briefing where conflicting.

Fleet path: Path C — Max 20x 4-agent full fleet (+$200/mo). Supersedes the 5/21 lock of Path A. Intentional billing upgrade. Anthropic billing change still to be executed by John.

Domain: azuresb.com / app.azuresb.com (purchased 2026-05-21 via Cloudflare Registrar, $10.46/yr). Frontend live on Cloudflare Pages. Apex azuresb.com not yet wired to Pages (optional).

Region: Falkenstein, DE (Hetzner CPX32, Ubuntu 26.04, IP 178.105.154.183, backups on, $20.39/mo). Live since 2026-05-21. EU latency ~150ms from California accepted for pregame-only refresh.

Teammate: yes — John has someone in mind. Name TBD. Action items: 30-min comp call, GitHub seat on the gridv2 repo, lane assignment in PROJECT.md, branch namespace (e.g., friend/*).

OddsPapi ToS email: submitted 2026-05-21 via oddspapi.io/us/contact. No reply yet. John leaning toward purchasing the Normal tier ($57/mo) without waiting for the reply.

Brand: user-facing name is Azure Sportsbook. Internal codename stays GridV2 (repo, PROJECT.md, briefings).

Briefing producer (interim): stays manual / on-demand until runbook 03 (stack install — Node 20 / Postgres 16 / Caddy / Claude Code) lands and the agent fleet on the VPS can write briefings as its closing task.

Next session (per 5/21 GridV2 briefing): draft runbooks/03-stack-install.md and execute on the VPS so api.azuresb.com returns 200 from /health. After that, Phase 0 is fully closed and Phase 1 backend code can start.

## 11.8 Teammate decision flipped (2026-05-22, same session)

After §11.7 locked the six Phase 0 decisions with "teammate = yes" (name TBD), the same session continued into a plan-comparison exercise that flipped this decision before any teammate prep work was done.

Trigger: John asked for help setting up infrastructure for the teammate, assuming an Anthropic organization had to be created and the teammate invited. Research revealed Anthropic's Team plan has a 5-seat minimum and each Premium seat is capped at 6.25x Pro usage — less than what Max 20x personal ($200/mo) gives a single user (20x Pro). For 2 actual users, the Team plan wastes 3 seats AND downgrades per-user capacity. Two personal Max 20x subscriptions ($400/mo combined) would be both cheaper and higher-capacity than the equivalent Team setup.

Locked decision: proceed solo with one personal Max 20x ($200/mo). No GitHub collaborator invite, no friend/* branch namespace, no shared VPS SSH key, no Anthropic org setup. Teammate revisited post-MVP if scope expands. Fleet path C (Max 20x 4-agent) still stands — fleet sizing is about token capacity, not headcount.

Net effect on roadmap: §11.7 bullet 4 (Teammate) is superseded by this section. All other Phase 0 decisions (domain, region, fleet path C, brand, briefing producer) unchanged. Phase 0 infrastructure (runbooks 03 + 04) was already executed overnight 5/21 — stack is live at api.azuresb.com. Remaining Phase 0 work is now: Max 20x upgrade (in progress), runbook 06 (Claude Code on VPS), runbook 07 (fleet orchestration), buy OddsPapi, draft AUTH_DESIGN.md.